# Professional Project Plan

## Smart Multi-Vendor Inventory API with AI Forecasting

# 1. Executive Summary

Project Name: Smart Multi-Vendor Inventory API (SMVIA)

Project Duration: 8 Weeks

Project Budget: $0 (Open-source/Personal Investment)

Overview:
The Smart Multi-Vendor Inventory API is a cloud-native, multi-tenant inventory management system designed to serve multiple businesses through a single deployment instance. The platform provides vendors with real-time inventory tracking, role-based access control, and AI-powered demand forecasting to optimize stock levels and prevent stockouts.

Business Value:

- Enables SaaS providers to launch inventory management services for multiple clients with complete data isolation

- Reduces inventory carrying costs through AI-driven demand forecasting

- Automates stock replenishment recommendations based on historical sales patterns

- Provides scalable architecture that can grow from 1 to 1,000+ vendors without code changes

Strategic Significance:
This project demonstrates enterprise-grade software engineering practices including multi-tenancy, asynchronous task processing, machine learning integration, and production-ready API design. For a junior developer, this project bridges the gap between basic CRUD applications and the complex, scalable systems required in modern tech companies.

# 2. Project Objectives

| ID | Objective | Success Metric | Target |
| --- | --- | --- | --- |
| O1 | Implement secure multi-tenancy with complete data isolation | Zero data leaks between test vendors | 100% isolation in testing |
| O2 | Build RESTful API with comprehensive CRUD operations | API endpoints for all core resources | 25+ endpoints |
| O3 | Achieve 90%+ test coverage for critical paths | Test coverage report | >90% |
| O4 | Implement JWT authentication with OTP verification | Successful auth flow | <3s verification time |
| O5 | Deploy Celery-based background task processing | Async task completion rate | >99% |
| O6 | Integrate ML-based demand forecasting | Forecast accuracy | >80% accuracy |
| O7 | Containerize application with Docker | One-command deployment | Success on any machine |
| O8 | Create comprehensive API documentation | OpenAPI/Swagger spec | 100% endpoints documented |

# 3. Scope Statement

## 3.1 In Scope

Core Features:

- Multi-tenant architecture supporting unlimited vendors

- Row-level data isolation between tenants

- JWT-based authentication with email OTP verification

- Role-based access control (Vendor Admin, Staff, Viewer)

- Complete inventory management (Products, Categories, Stock Levels)

- Sales transaction recording and history

- Supplier management

- Purchase order generation

- RESTful API with versioning (v1, future v2 planning)

- API rate limiting per vendor tier

Technical Implementation:

- Django 4.2+ with Django REST Framework

- PostgreSQL database with tenant-specific schemas

- Redis caching and message brokering

- Celery for background task processing

- Docker containerization with docker-compose

- Unit and integration testing suite

- Swagger/OpenAPI documentation

AI/ML Features:

- Demand forecasting using statistical models (Exponential Smoothing)

- Low stock alerts based on predicted demand

- Automated reorder recommendations

## 3.2 Out of Scope

- Frontend dashboard or UI (API-only)

- Mobile applications

- Payment processing integration

- Billing/subscription management

- Real-time WebSocket updates

- Third-party e-commerce platform integrations (Shopify, WooCommerce)

- Barcode/RFID hardware integration

- Multi-language support

- Mobile push notifications

- Advanced analytics dashboard

- Import from legacy systems

- PCI compliance for credit card processing

# 4. Project Deliverables

| Deliverable ID | Deliverable Name | Description | Acceptance Criteria |
| --- | --- | --- | --- |
| D1 | Technical Architecture Document | Detailed system design including database schema, API structure, and component interactions | Reviewed and approved by technical lead |
| D2 | Multi-Tenancy Implementation | Core tenant isolation system with middleware and custom model managers | All queries automatically filtered by tenant; zero data leaks in testing |
| D3 | Authentication Module | JWT-based auth with OTP email verification and role management | Successful login, token refresh, and role-based access control |
| D4 | Core Data Models | Product, Category, Inventory, Sale, Supplier models with relationships | All models implemented with proper foreign keys and indexes |
| D5 | REST API Endpoints | Complete CRUD API for all resources | 25+ endpoints with proper status codes, validation, and error handling |
| D6 | Background Task System | Celery configuration with Redis broker and result backend | Tasks execute asynchronously; task status trackable |
| D7 | AI Forecasting Engine | Demand prediction module with reorder recommendations | Forecast generated for products with >30 days of history |
| D8 | API Documentation | Swagger/OpenAPI documentation with examples | All endpoints documented with request/response examples |
| D9 | Test Suite | Unit and integration tests | >90% code coverage; all tests passing |
| D10 | Docker Configuration | Dockerfiles and docker-compose for local development | One-command docker-compose up runs complete stack |
| D11 | Deployment Guide | Step-by-step deployment instructions | Successfully deployed to test environment |
| D12 | Project Repository | GitHub repository with commit history and README | Public access; clear README with setup instructions |

# 5. Project Phases

## Phase 1: Foundation & Architecture (Week 1)

Description: Establish project foundation, development environment, and core architectural patterns. This phase ensures all subsequent development follows consistent standards and best practices.

| Task # | Task Name | Description | Status |
| --- | --- | --- | --- |
| 1.1 | Project Setup | Initialize Django project, configure virtual environment, set up version control | Pending |
| 1.2 | Database Design | Create ER diagrams, define core models relationships, plan indexing strategy | Pending |
| 1.3 | Multi-Tenancy Strategy | Research and decide on tenant isolation approach (row-level vs schema-based) | Pending |
| 1.4 | Development Standards | Establish coding standards, commit message conventions, branch strategy | Pending |
| 1.5 | Environment Configuration | Set up development, testing, and production environment variables | Pending |
| 1.6 | Initial Django Configuration | Configure settings, install required packages, set up database connection | Pending |
| 1.7 | Docker Initialization | Create Dockerfile and docker-compose.yml for local development | Pending |

## Phase 2: User Authentication & Multi-Tenancy (Week 2)

Description: Implement the core security and isolation features that form the foundation of the multi-tenant platform.

| Task # | Task Name | Description | Status |
| --- | --- | --- | --- |
| 2.1 | Custom User Model | Extend Django's AbstractUser to include role field and vendor relationship | Pending |
| 2.2 | Vendor Model | Create Vendor model with business details and subdomain field | Pending |
| 2.3 | Tenant Middleware | Build middleware to detect tenant from subdomain/header and set thread-local | Pending |
| 2.4 | Custom Model Managers | Create VendorAwareManager to automatically filter querysets by tenant | Pending |
| 2.5 | JWT Authentication | Configure SimpleJWT for token-based authentication | Pending |
| 2.6 | OTP Email Verification | Implement email OTP generation, storage, and verification flow | Pending |
| 2.7 | Role-Based Permissions | Create custom permission classes for vendor, staff, and customer roles | Pending |
| 2.8 | Signup Endpoints | Build separate registration endpoints for vendors and customers | Pending |
| 2.9 | Email Integration | Configure email backend for OTP and welcome emails | Pending |

## Phase 3: Core Inventory Models (Week 3)

Description: Build the data models and basic CRUD operations for inventory management.

| Task # | Task Name | Description | Status |
| --- | --- | --- | --- |
| 3.1 | Category Model | Create Category model with vendor foreign key and unique constraints | Pending |
| 3.2 | Product Model | Implement Product model with SKU, pricing, and type fields | Pending |
| 3.3 | Inventory Model | Create Inventory model with quantity, reorder level, and last restocked | Pending |
| 3.4 | Supplier Model | Build Supplier model with contact information | Pending |
| 3.5 | Sale Model | Implement Sale model to track transactions | Pending |
| 3.6 | Purchase Order Model | Create PurchaseOrder model for restocking | Pending |
| 3.7 | Database Migrations | Generate and test all database migrations | Pending |
| 3.8 | Model Admin Configuration | Set up Django admin for all models with tenant filtering | Pending |
| 3.9 | Data Validation | Add model-level validation and clean methods | Pending |

## Phase 4: REST API Development (Week 4)

Description: Expose all functionality through a well-designed, versioned REST API.

| Task # | Task Name | Description | Status |
| --- | --- | --- | --- |
| 4.1 | API Structure Design | Plan URL structure, versioning strategy, and response formats | Pending |
| 4.2 | Serializers | Create serializers for all models with nested relationships | Pending |
| 4.3 | Category Endpoints | Implement CRUD for categories with tenant filtering | Pending |
| 4.4 | Product Endpoints | Build product endpoints with search and filtering | Pending |
| 4.5 | Inventory Endpoints | Create inventory-specific endpoints (adjust, transfer, count) | Pending |
| 4.6 | Sale Endpoints | Implement sales recording and history retrieval | Pending |
| 4.7 | Supplier Endpoints | Build supplier management endpoints | Pending |
| 4.8 | Purchase Order Endpoints | Create PO creation and tracking endpoints | Pending |
| 4.9 | Custom Actions | Add @action endpoints for reports and bulk operations | Pending |
| 4.10 | Pagination | Implement pagination for list endpoints | Pending |
| 4.11 | Filtering & Search | Add django-filter integration for advanced querying | Pending |
| 4.12 | Error Handling | Create consistent error response format | Pending |
| 4.13 | API Versioning | Set up URL-based versioning (v1, future v2) | Pending |

## Phase 5: Celery & Background Processing (Week 5)

Description: Implement asynchronous task processing for report generation, email sending, and AI model execution.

| Task # | Task Name | Description | Status |
| --- | --- | --- | --- |
| 5.1 | Celery Configuration | Set up Celery with Redis broker and result backend | Pending |
| 5.2 | Django-Celery-Results | Configure database backend for task results | Pending |
| 5.3 | Email Tasks | Move email sending to async tasks | Pending |
| 5.4 | Report Generation | Create CSV/PDF report generation as background tasks | Pending |
| 5.5 | Scheduled Reports | Implement periodic tasks for weekly/monthly reports | Pending |
| 5.6 | Task Monitoring | Set up Flower for task monitoring | Pending |
| 5.7 | Retry Logic | Implement automatic retries for failed tasks | Pending |
| 5.8 | Task Chaining | Create complex workflows with task chains | Pending |
| 5.9 | Rate Limiting | Add task rate limiting for external APIs | Pending |
| 5.10 | Task Status API | Build endpoints to check task status | Pending |

## Phase 6: AI Forecasting Module (Week 6)

Description: Integrate machine learning capabilities for demand forecasting and inventory optimization.

| Task # | Task Name | Description | Status |
| --- | --- | --- | --- |
| 6.1 | Data Preparation | Create functions to prepare sales data for modeling | Pending |
| 6.2 | Statistical Analysis | Research and select appropriate forecasting models | Pending |
| 6.3 | Prophet Integration | Implement Facebook Prophet for time series forecasting | Pending |
| 6.4 | Model Training | Create background tasks for model training | Pending |
| 6.5 | Forecast Storage | Store forecast results in database | Pending |
| 6.6 | Forecast API Endpoint | Build endpoint to retrieve forecasts | Pending |
| 6.7 | Reorder Recommendations | Calculate reorder points based on forecasts | Pending |
| 6.8 | Low Stock Alerts | Generate alerts for products below reorder level | Pending |
| 6.9 | Accuracy Tracking | Log forecast accuracy for continuous improvement | Pending |
| 6.10 | Batch Forecasting | Create task to forecast all vendor products | Pending |

## Phase 7: Testing & Quality Assurance (Week 7)

Description: Ensure reliability, security, and performance through comprehensive testing.

| Task # | Task Name | Description | Status |
| --- | --- | --- | --- |
| 7.1 | Unit Test Setup | Configure pytest and test database | Pending |
| 7.2 | Model Tests | Test all model methods and validations | Pending |
| 7.3 | Multi-Tenancy Tests | Verify complete data isolation between vendors | Pending |
| 7.4 | Authentication Tests | Test login, OTP, token refresh flows | Pending |
| 7.5 | Permission Tests | Verify role-based access control | Pending |
| 7.6 | API Endpoint Tests | Test all endpoints with valid/invalid data | Pending |
| 7.7 | Celery Task Tests | Test async task execution and results | Pending |
| 7.8 | Integration Tests | Test complete workflows (create product → record sale → forecast) | Pending |
| 7.9 | Performance Testing | Test API response times under load | Pending |
| 7.10 | Security Testing | Scan for common vulnerabilities | Pending |
| 7.11 | Coverage Report | Generate and review test coverage | Pending |

## Phase 8: Documentation & Deployment (Week 8)

Description: Prepare project for public release and create comprehensive documentation.

| Task # | Task Name | Description | Status |
| --- | --- | --- | --- |
| 8.1 | API Documentation | Generate Swagger/OpenAPI spec with drf-yasg | Pending |
| 8.2 | README | Create comprehensive README with setup instructions | Pending |
| 8.3 | Deployment Guide | Write step-by-step deployment documentation | Pending |
| 8.4 | Postman Collection | Create and export Postman collection for API testing | Pending |
| 8.5 | Docker Optimization | Optimize Dockerfile for production | Pending |
| 8.6 | Production Deployment | Deploy to cloud platform (Render/Heroku/DigitalOcean) | Pending |
| 8.7 | Domain Configuration | Set up subdomain routing for tenants | Pending |
| 8.8 | SSL Certificate | Configure HTTPS | Pending |
| 8.9 | Environment Variables | Set up production environment configuration | Pending |
| 8.10 | Final Review | Complete project review and bug fixes | Pending |
| 8.11 | GitHub Release | Create v1.0.0 release | Pending |

# 6. Timeline

## Gantt Chart (Weekly View)

| Phase | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Phase 1: Foundation | ██████ |  |  |  |  |  |  |  |
| Phase 2: Auth & Multi-Tenancy |  | ██████ |  |  |  |  |  |  |
| Phase 3: Core Models |  |  | ██████ |  |  |  |  |  |
| Phase 4: REST API |  |  |  | ██████ |  |  |  |  |
| Phase 5: Celery |  |  |  |  | ██████ |  |  |  |
| Phase 6: AI Forecasting |  |  |  |  |  | ██████ |  |  |
| Phase 7: Testing |  |  |  |  |  |  | ██████ |  |
| Phase 8: Documentation |  |  |  |  |  |  |  | ██████ |

## Milestone Table

| Milestone | Due Date | Deliverable |
| --- | --- | --- |
| Project Foundation Complete | End of Week 1 | Dockerized Django app with database |
| Multi-Tenancy Implemented | End of Week 2 | Tenant isolation working; auth complete |
| Core Models Complete | End of Week 3 | All database models with migrations |
| API v1 Complete | End of Week 4 | All CRUD endpoints functional |
| Async Processing Ready | End of Week 5 | Celery tasks working; Flower accessible |
| AI Forecasting Functional | End of Week 6 | Forecasts generated for test products |
| Test Suite Complete | End of Week 7 | >90% coverage; all tests passing |
| Production Release | End of Week 8 | Live API with documentation |

# 7. Resources

## 7.1 Team Members

| Role | Name | Responsibility | Commitment |
| --- | --- | --- | --- |
| Project Lead/Developer | [Your Name] | Overall architecture, development, deployment | Full-time (40 hrs/week) |
| Technical Advisor | Mentor/Peer | Code reviews, technical guidance | Part-time (2 hrs/week) |

## 7.2 Tools & Software

| Category | Tool | Purpose | Cost |
| --- | --- | --- | --- |
| Development |  |  |  |
| IDE | VS Code / PyCharm | Code editing | Free |
| Version Control | Git + GitHub | Source code management | Free |
| API Testing | Postman | API development and testing | Free |
| Database GUI | pgAdmin / DBeaver | Database management | Free |
| Infrastructure |  |  |  |
| Containerization | Docker Desktop | Local container runtime | Free |
| Cloud Hosting | Render / PythonAnywhere | Production deployment | Free tier available |
| Database | PostgreSQL (via Render) | Production database | Free tier available |
| Cache/Queue | Redis (via Redis Labs) | Caching and message broker | Free tier available |
| Monitoring |  |  |  |
| Task Monitoring | Flower | Celery task monitoring | Free |
| Error Tracking | Sentry | Error monitoring (optional) | Free tier |
| Productivity |  |  |  |
| Project Management | GitHub Projects | Task tracking | Free |
| Documentation | Markdown + Swagger | Technical documentation | Free |
| Diagramming | Draw.io / Lucidchart | Architecture diagrams | Free |

## 7.3 Budget

| Item | Cost | Notes |
| --- | --- | --- |
| Domain Name | $10-15/year | Optional - can use platform subdomain |
| Cloud Hosting | $0-7/month | Free tiers available; scale as needed |
| Email Service | $0 | Use free tier of SendGrid or Gmail SMTP |
| Total | $10-22/year | Minimal investment required |

# 8. Roles & Responsibilities

| Role | Responsibilities | Accountabilities |
| --- | --- | --- |
| Project Lead | • Architect the overall system • Write all code and tests • Make technical decisions • Manage git repository • Deploy and maintain production • Document the project | • Delivering working software • Meeting project timeline • Code quality and standards • Project success |
| Technical Advisor | • Review architecture decisions • Provide code feedback • Suggest best practices • Help troubleshoot blockers | • Quality of technical guidance • Timely feedback |
| End User (Simulated) | • Test the API from vendor perspective • Provide usability feedback • Report bugs | • Honest feedback • Thorough testing |

# 9. Risk Management Plan

| Risk ID | Risk Description | Probability | Impact | Mitigation Strategy | Contingency Plan |
| --- | --- | --- | --- | --- | --- |
| R1 | Data leak between tenants | Low | Critical | • Implement and test row-level security rigorously • Write specific multi-tenancy tests • Use custom model managers for all queries | Immediate rollback; data audit; fix isolation bug |
| R2 | Celery task failures | Medium | Medium | • Implement retry logic with exponential backoff • Monitor tasks with Flower • Log all failures | Manual task rerun; fix underlying issue |
| R3 | AI model accuracy too low | Medium | Medium | • Start with simple statistical models • Benchmark multiple algorithms • Set realistic expectations | Fall back to simple reorder point calculation |
| R4 | Project timeline slippage | High | Medium | • Prioritize core features first • Use agile methodology • Track progress weekly | Cut non-critical features; extend timeline |
| R5 | Technical complexity overwhelming | Medium | High | • Break down complex tasks • Research thoroughly before coding • Seek mentor guidance | Simplify approach; revisit architecture |
| R6 | Low test coverage | Medium | Medium | • Write tests alongside code (TDD where possible) • Enforce coverage requirements • Review coverage weekly | Dedicate final week to test improvement |
| R7 | Deployment issues | Medium | Medium | • Use Docker for consistency • Test deployment early • Document all steps | Roll back to previous version; debug incrementally |
| R8 | Burnout/loss of motivation | Medium | High | • Set realistic daily goals • Take regular breaks • Celebrate small wins | Take planned breaks; adjust scope |

# 10. Stakeholder Analysis

## 10.1 Stakeholder Identification

| Stakeholder | Interest in Project | Influence | Expectations |
| --- | --- | --- | --- |
| You (Project Lead) | High - Portfolio piece, skill development | High | Complete project, learn new skills, create impressive demo |
| Potential Employers | Medium - Evaluate technical abilities | Medium | See clean code, proper architecture, documentation |
| Technical Community | Low - Open source users | Low | Usable code, good documentation |
| Mentor/Peer | Medium - Help you succeed | Medium | Clear communication, responsiveness to feedback |
| Future Users | Low - Not yet identified | Low | Functional API, clear documentation |

## 10.2 Communication Plan

| Stakeholder | Communication Method | Frequency | Content |
| --- | --- | --- | --- |
| Project Lead | Self-review, project board | Daily | Task progress, blockers, next steps |
| Potential Employers | GitHub repository, README | Upon completion | Code quality, documentation, demo |
| Technical Community | GitHub issues, documentation | As needed | Bug reports, feature requests |
| Mentor/Peer | Video call, chat | Weekly | Progress update, code review, blockers |
| General Public | Blog posts (optional) | Upon completion | Project journey, lessons learned |

# 11. Project Monitoring & Control

## 11.1 Progress Tracking Methods

| Method | Description | Frequency |
| --- | --- | --- |
| Daily Task Log | Track completed tasks, time spent, and blockers | Daily |
| GitHub Commit History | Monitor code velocity and focus areas | Continuous |
| Phase Completion Reviews | Verify phase deliverables before moving forward | End of each phase |
| Test Coverage Reports | Monitor code quality metric | Weekly |
| Burn-down Chart | Track remaining tasks vs. timeline | Weekly |

## 11.2 Quality Control Measures

| Measure | Target | Monitoring Method |
| --- | --- | --- |
| Code Coverage | >90% | Coverage.py report |
| Test Pass Rate | 100% | pytest results |
| API Response Time | <200ms for reads, <500ms for writes | Manual testing + profiling |
| Code Style | PEP 8 compliant | flake8 / black |
| Documentation Completeness | 100% endpoints documented | Swagger UI review |

## 11.3 Reporting Structure

Weekly Status Report Template:

text

# Weekly Status Report - Week [X]

## Accomplished This Week

- [Task 1] - Completed

- [Task 2] - In Progress

- [Task 3] - Started

## Metrics

- Test Coverage: [XX]%

- Tasks Completed: [X] of [Y]

- Hours Invested: [XX]

## Blockers

- [Blocker 1] - Mitigation: [Plan]

## Next Week's Goals

- [Goal 1]

- [Goal 2]

## Risk Update

- [Risk ID]: Status unchanged/mitigated/increased

## 11.4 Success Criteria

The project will be considered successfully completed when:

- All Phase 8 deliverables are complete - Documentation, deployment, final review

- Test coverage exceeds 90% - Verified by coverage report

- All critical path tests pass - Multi-tenancy tests specifically

- API is publicly accessible - Live demo available

- Forecasting module produces reasonable predictions - Verified with test data

- GitHub repository is public - With comprehensive README

- Postman collection works - New users can test API easily

# 12. Approval

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Lead | [Your Name] |  |  |
| Technical Advisor | [Mentor Name] |  |  |

Document Version: 1.0
Last Updated: [Current Date]
Status: Draft for Review